# Energy in Our Life

## Project meeting in Darica, 3rd-8th May 2011

# Evaluation report - evaluation of the first project year

- All schools took part in the project meetings in Brno, Las Palmas and Darica.

- According to the “Calendar of activities” and according to the “Plan of the first year” (see the application or eiol.wz.cz) all schools involved have fulfilled the planned tasks:

  - creating Comenius teams at schools

  - setting up a website at each school

  - online researches on national energy/coal/oil/gas resources

  - questioning, processing research

  - meeting with local resources experts

  - winter consumption measurements at home and at school + evaluation

  - visiting a power station, heating plant etc

- The global portfolio is complete and available on eiol.wz.cz:

  - plan of the first year

  - comparison of  resources in different countries

  - article on sustained management of the resources

  - questionnaire on resources aspects

  - comparison of results of questionings

- Each school should upload some photos from the meetings.

- Each school will start the summer measurements immediately – it would be good if the same houses/flats were involved.

- Each school will prepare/complete its notice board.

- The project meeting in Palermo will take part from 20th to 25th October 2011. The Italian school offers to accept three teachers from each country. The main task for Palermo is to compare and contrast the winter and summer measurements (presentation by students), to agree on the topics for CLIL and to plan further activities for the second project year.